## Sheet 1 - Threats Sheet
Threats Sheet
Threat ID | STRIDE Category | DFD Element/Flow | Threat Description | Likelihood (L) | Impact (I) | Risk Score (R) | Mitigation | Owner | Effort | Status | Target Sprint
T01 | Information Disclosure | Frontend and Firebase Auth | Incomplete Firebase ID token validation (no issuer/audience/expiry checks) | 3 | 5 | 4 | Verify issuer audience and expiry claims using Firebase Admin SDK server-side | Frontend Team | Medium | Planned | 11
T02 | Information Disclosure | Frontend and Firestore | Overly permissive Firestore Security Rules in test mode allow all reads/writes | 3 | 5 | 4 | Implement production Security Rules with document-level ownership checks | Backend Team | Medium | Planned | 11
T03 | Information Disclosure | Frontend to TMDB API | TMDB API key exposed in client bundle visible in source code | 4 | 3 | 3.5 | Proxy API calls through backend service rotate keys regularly enforce quotas | Backend Team | Medium | In Progress | 12
T04 | Information Disclosure | Frontend Client | PII (email userId) exposed in client-side logs and analytics (Google Analytics) | 3 | 4 | 3.5 | Redact sensitive fields minimize data collection enforce retention policies | Frontend Team | Small | Planned | 12
T05 | Elevation of Privilege | Frontend and Firestore | Inadequate Firestore document ownership validation allows cross-user access | 3 | 4 | 3.5 | Add authentication checks in Security Rules: request.auth.uid == resource.data.userId | Backend Team | Small | Planned | 12
T06 | Denial of Service | Frontend to TMDB API | TMDB API rate limit exhaustion from unlimited client requests | 4 | 3 | 3.5 | Implement client-side throttling response caching quota monitoring | Frontend Team | Medium | Planned | 13
T07 | Spoofing | Frontend and Firebase Auth | Weak Firebase password policy allows easy credential guessing | 2 | 4 | 3 | Enforce minimum 12-character passwords with complexity requirements | Backend Team | Small | Planned | 13
T08 | Denial of Service | Frontend and Firestore | Firestore mass document creation attack (no write rate limits) | 3 | 3 | 3 | Implement write rate limits in Security Rules usage monitoring alerts | Backend Team | Medium | Backlog | 14
T09 | Tampering | Frontend and TMDB API | Man-in-the-middle tampering of TMDB metadata in transit | 2 | 4 | 3 | Enforce HTTPS implement Subresource Integrity for CDN assets | DevOps Team | Small | Done | 10
T10 | Spoofing | Frontend and Firebase Auth | Email enumeration via sign-up error messages reveals valid accounts | 4 | 2 | 3 | Return generic error messages implement CAPTCHA on sign-up | Frontend Team | Small | Planned | 13
T11 | Repudiation | Frontend and Firebase Auth | Insufficient audit logging of authentication events | 2 | 3 | 2.5 | Enable Firebase Auth logging integrate with SIEM | DevOps Team | Medium | Backlog | 15
T12 | Information Disclosure | Frontend | Session tokens stored in localStorage (not httpOnly cookies) | 3 | 2 | 2.5 | Migrate to httpOnly secure cookies for token storage | Frontend Team | Medium | Backlog | 15
T13 | Denial of Service | Frontend | No client-side input validation allows malformed requests | 3 | 2 | 2.5 | Implement client-side validation sanitization library | Frontend Team | Small | Backlog | 16
T14 | Tampering | Frontend and Firestore | No integrity checks on Firestore document contents | 2 | 3 | 2.5 | Implement document checksums or digital signatures | Backend Team | Large | Backlog | 17
T15 | Information Disclosure | Frontend | Verbose error messages leak internal system details | 3 | 2 | 2.5 | Implement generic user-facing errors log details server-side | Frontend Team | Small | Backlog | 16
T16 | Spoofing | Frontend | No protection against session fixation attacks | 2 | 3 | 2.5 | Regenerate session tokens after authentication | Frontend Team | Small | Backlog | 16
T17 | Denial of Service | Frontend | No protection against browser storage quota exhaustion | 2 | 2 | 2 | Implement storage limits cleanup policies | Frontend Team | Small | Backlog | 17
T18 | Repudiation | Frontend and Firestore | No audit trail for favorites CRUD operations | 2 | 2 | 2 | Add Firestore audit logging with timestamps and userIds | Backend Team | Medium | Backlog | 18
T19 | Information Disclosure | TMDB API | TMDB API returns more data than needed (over-fetching) | 2 | 2 | 2 | Request only required fields implement response filtering | Frontend Team | Small | Backlog | 18
T20 | Elevation of Privilege | Frontend | No role-based access control (all users have same permissions) | 1 | 3 | 2 | Implement RBAC with admin/user roles | Backend Team | Large | Future | N/A
T21 | Tampering | Frontend | No Content Security Policy headers | 2 | 2 | 2 | Implement CSP headers to prevent XSS | DevOps Team | Small | Backlog | 17
T22 | Spoofing | Frontend and Firebase Auth | No multi-factor authentication option | 1 | 3 | 2 | Enable Firebase MFA for high-security accounts | Backend Team | Medium | Future | N/A
T23 | Denial of Service | Frontend | No rate limiting on search queries | 2 | 2 | 2 | Implement debouncing on search input rate limit queries | Frontend Team | Small | Backlog | 17